## Sheet1
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By | Owned By | Comment | Comment | Comment | Comment | Comment | Comment
134759533 | Add new employee |  | 1 | 2016-11-21 | 2016-11-27 | feature | 3 | accepted | 2016-11-21 | 2016-11-27 |  | jiloong | As a admin, I want to create a new employee with following details such as staff ID, name, identity card number, address, position (departmental manager, doctor, nurse, clerk), salary, contact number, login details (login ID and password) and etc. So that, i can add new employee into the system. Acceptance Criteria 1 Given that all the new employee's details has been filled When admin select create a new employee Then ensure that the employee is not duplicate in the database And ensure that the employee details are saved into the database Acceptance Criteria 2 Given that all the new employee's details has been filled but the employee details is duplicated When admin select create a new employee Then ensure the duplicate employee message will be displayed to admin And ensure the details are not create into the database. Acceptance Criteria 3 Given that the user does not has sufficient privilege or roles level as admin When user create a new employee Then ensure that error message is prompted to user And ensure the details are not create into the database. | https://www.pivotaltracker.com/story/show/134759533 | jiloong | Jin | Eric Tam | Can i know what roles can add employee details? (Weng Hong - Nov 27, 2016) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/513c104471c84124c2efbcf5363de5f4ec353b0d Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#134759533], [Add new employee] (jiloong - Jan 6, 2017) | Commit by siaoteh https://github.com/siaoteh/HospitalManagementSystem/commit/c31c46617bfb260369aee117e914f853d45d88e0 Add files via upload 1_Developers: [Yong Weng Hong] 2_Time: [2 hours] 3_Use_case: [#134759533],[#134759533],[Add new employee] (jiloong - Jan 6, 2017)