## Sheet1
Id | Title | Labels | Iteration | Iteration Start | Iteration End | Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Description | URL | Owned By | Owned By | Owned By | Comment | Comment | Comment | Comment | Comment | Comment
134759533 | Add new employee |  | 1 | 2016-11-21 | 2016-11-27 | feature | 3 | accepted | 2016-11-21 | 2016-11-27 |  | jiloong | As a admin, I want to create a new employee with following details such as staff ID, name, identity card number, address, position (departmental manager, doctor, nurse, clerk), salary, contact number, login details (login ID and password) and etc. So that, i can add new employee into the system. Acceptance Criteria 1 Given that all the new employee's details has been filled When admin select create a new employee Then ensure that the employee is not duplicate in the database And ensure that the employee details are saved into the database Acceptance Criteria 2 Given that all the new employee's details has been filled but the employee details is duplicated When admin select create a new employee Then ensure the duplicate employee message will be displayed to admin And ensure the details are not create into the database. Acceptance Criteria 3 Given that the user does not has sufficient privilege or roles level as admin When user create a new employee Then ensure that error message is prompted to user And ensure the details are not create into the database. | https://www.pivotaltracker.com/story/show/134759533 | jiloong | Jin | Eric Tam | Can i know what roles can add employee details? (Weng Hong - Nov 27, 2016) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/513c104471c84124c2efbcf5363de5f4ec353b0d Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#134759533], [Add new employee] (jiloong - Jan 6, 2017) | Commit by siaoteh https://github.com/siaoteh/HospitalManagementSystem/commit/c31c46617bfb260369aee117e914f853d45d88e0 Add files via upload 1_Developers: [Yong Weng Hong] 2_Time: [2 hours] 3_Use_case: [#134759533],[#134759533],[Add new employee] (jiloong - Jan 6, 2017)
135113027 | Patient Registration |  | 5 | 2016-12-19 | 2016-12-25 | feature | 3 | started | 2016-11-29 |  |  | Weng Hong | As a hospital admission staff, I'm able to add a new patient details such as patient ic number, name, contact number, address, fingerprint, sickness history(if any) and etc. Besides that, I also allowed to view/update patient details. Acceptance Criteria 1 - Add Patient Details Given that all the new patient details that has been filled When patient insert his/her identity card into a card reader Then the reader will capture patient identical card personal details such as name, ic no, address and race And admission staff will also require patient others particular details such as contact number, email in order to keep track with patient if needed. Patient are required to confirm above details are correct before admission staff register details into hospital database. Acceptance Criteria 2 - Generate Patient Smart Card Given that the patient details such as patient ic number, name, contact number, address, fingerprint, sickness history(if any) and etc has been filled, system will generate a card called "Patient Smart Card" to patient When patient registration successful during first time visition Then system will generate a patient smart card And patient will receive the smart card from admission counter Acceptance Criteria 3 - Patient Smart Card Function Given that patient own with a patient smart card When in the future, patient only need to insert smart card into nearest hospital kiosk and system will automatic retrieve patient details to admission staff for visitation process Then system will prompt out few service option to patient and patient required to select one of the services in the system And system will generate the queue number to patient once patient selected his/her option. Visitation process consider successful once patient follow above step Acceptance Criteria 4 - Update Patient Details Given that a particular patient request for update details When patient wish to update their details Then they need go to hospital admission counter request admission staff help for update details And admission staff will update latest patient details into system once all given details confirmed by patient. | https://www.pivotaltracker.com/story/show/135113027 | Weng Hong | jiloong |  | Commit by chashjin https://github.com/siaoteh/HospitalManagementSystem/commit/2d880a455180725c59816412d90a38df8ec7d8d2 Add files via upload 1_Developers: [Tan Ji Long] 2_Time: [2Hours] 3_Use_case: [#135113027], [Patient Registration] (jiloong - Jan 5, 2017) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/7f7c1d055e6d712b5564cacc4affe25ad8cbd4f6 Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#135113027], [Patient Registration] (jiloong - Jan 6, 2017) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/de27ecc93c05bbeac0921c8ccfc20e3a532d3c1e Add files via upload 1_Developers: [Soh Kok Jin], [Tan Ji Long] 2_Time: [2Hours] 3_Use_case: [#135113027], [Patient Registration] (jiloong - Jan 6, 2017)
135113617 | Edit Employee details |  | 5 | 2016-12-19 | 2016-12-25 | feature | 2 | started | 2016-11-29 | 2016-12-25 |  | Eric Tam | As a user, I want to edit an employee's details, So that, i can correct the employee's details. Acceptance Criteria 1 Given that user's corrected details is valid When user select update details. Then ensure that the details are updated into the database and prompt update successfully message. Acceptance Criteria 2 Given that user's corrected details is invalid When user select update details Then ensure the error message is prompted And make sure the details is not update to the database. Acceptance Criteria 3 Given that the user's details does not belong to the user When user update the details Then ensure that the user unable to edit other employee's details | https://www.pivotaltracker.com/story/show/135113617 | jiloong |  |  | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/6853b9d1e1a3231dfe7eec659167c0bf6b60c626 Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#135113617], [Edit Employee details] (jiloong - Jan 6, 2017) | Commit by siaoteh https://github.com/siaoteh/HospitalManagementSystem/commit/e2aa021d0b20bc188d27c06ce821f7b0c410e8a4 Add files via upload 1_Developers: [Yong Weng Hong] 2_Time: [2 hours] 3_Use_case: [#135113617],[#135114069], [Edit Employee details] (jiloong - Jan 6, 2017)
135114069 | View employee details |  | 5 | 2016-12-19 | 2016-12-25 | feature | 1 | started | 2016-11-29 |  |  | Eric Tam | As a user, I want to view a new employees' details So that, i can ensure the employee's details is valid. Acceptance Criteria 1 Given that the employee's details is exist When user select view employee details Then ensure system will search the employee's details from the database And show the employee's details Acceptance Criteria 2 Given that the employee's details does not exist When user select view a employee details Then ensure that the error message is displayed to user. Acceptance Criteria 3 Given that the employee's details does not belong to the user When user select view a employee details Then ensure will not show the employee's details to user And show the error message | https://www.pivotaltracker.com/story/show/135114069 | jiloong |  |  | Commit by siaoteh https://github.com/siaoteh/HospitalManagementSystem/commit/e2aa021d0b20bc188d27c06ce821f7b0c410e8a4 Add files via upload 1_Developers: [Yong Weng Hong] 2_Time: [2 hours] 3_Use_case: [#135113617],[#135114069], [Edit Employee details] (jiloong - Jan 6, 2017)
135115071 | Ward Admission/Discharge Module |  | 6 | 2016-12-26 | 2017-01-01 | feature | 1 | started | 2016-11-29 |  |  | Jin | As a user, I am able to to view ward information such as staff available bed and schedule admission and admit a patient on the spot. Besides, I also able to keep track of the information that related to the costs and resources use by the patient during their stay. Then, I able to handle patient check out request once the doctor approve the patient request. Acceptance Criteria 1 - Checking In and View Information The staff able to view the ward information either in real time mode or online, staff can view available bed, schedule admission, then it also able to admit the patient on the spot, so that the staff can more effectively handle the use of the bed, staff and also clinic resources. Acceptance Criteria 2 - Resources Recording This module enable staff to track and recording all the information regarding to the cost and resources use by the patient during their stay, the data to be record include : medical, nursing care, pharmacy items, telephone costs, meals etc. Acceptance Criteria 3- Check Out function Staff able to check out the patient once they get the approval from the doctor, once the the staff check out the patient, the staff will update the status to checked out and update to the system, then system will change the the room to available. Acceptance Criteria 4- Patient Data Transfer After the patient check out, the staff will forward the patient admission fee and discharges fee to the payment module. | https://www.pivotaltracker.com/story/show/135115071 | Jin | jiloong |  | Commit by siaoteh https://github.com/siaoteh/HospitalManagementSystem/commit/d873f3f6114e3a9c12369bea99fc78c480e2e1ea Add files via upload 1_Developers: [Tan Ji Loong] 2_Time: [2 hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module] (jiloong - Jan 6, 2017) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/3a5238a4ffa8755695c3a18d03aebc7abf5e77db Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module ] (jiloong - Jan 6, 2017) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/51abc5a55df647243afc01503612abbce6dec618 Add files via upload 1_Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module] (jiloong - Jan 6, 2017) | Commit by erictam96 https://github.com/siaoteh/HospitalManagementSystem/commit/ac4c93875678f3772a49f81d853f858fa2bfe865 Add files via upload _Developers: [Tam Chee Yong] 2_Time: [2Hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module ] (jiloong - Jan 6, 2017) | Commit by chashjin https://github.com/siaoteh/HospitalManagementSystem/commit/52e9dbeb6277ab2304504a3710398c0f05702cc4 Add files via upload 1_Developers: [Soh Kok Jin], [Tan Ji Long] 2_Time: [2Hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module ] (jiloong - Jan 6, 2017) | Commit by chashjin https://github.com/siaoteh/HospitalManagementSystem/commit/3fadeebfa757bc8d55d68604c3066d26b3e95611 Add files via upload 1_Developers: [Soh Kok Jin], [Tan Ji Long] 2_Time: [2Hours] 3_Use_case: [#135115071], [Ward Admission/Discharge Module ] (jiloong - Jan 6, 2017)